## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
TA-01 | Create/Manage TA Profile | As a TA Applicant, I want to create and manage an exclusive profile, So that I can reuse this info for applications. | Must Have | 1 | 1. User can enter basic details. 2. Add skills. 3. Save and edit profile. | 3 | core function | 2026-03-10
TA-02 | Upload/Manage Resume | As a TA Applicant, I want to upload and manage my CV online, So that I can apply with up-to-date documents. | Must Have | 1 | 1. Upload CV files. 2. View current CV. 3. Replace/update CV. | 3 | core function
TA-03 | Centrally Search TA Jobs | As a TA Applicant, I want to centrally search for all available TA jobs, So that I can discover new opportunities easily. | Must Have | 1 | 1. View list of job postings. 2. Search by keywords/MO. 3. View job details. | 5 | core function
TA-04 | Apply for a TA Position | As a TA Applicant, I want to easily apply for a TA position, So that I can complete the process efficiently. | Must Have | 1 | 1. Click 'Apply' button. 2. System uses profile info automatically. 3. Receive confirmation. | 3 | core function
TA-05 | Track Application Status | As a TA Applicant, I want to track my real-time application progress, So that I can manage my expectations. | Must Have | 1 | 1. View list of applied jobs. 2. Display real-time status 3. View feedback notes. | 8 | core function, highest pain point
TA-06 | View Course & MO Details | As a TA Applicant, I want to see detailed info about the course and MO, So that I can assess my suitability. | Should Have | 2 | 1. Show MO's name. 2. Show module introduction. 3. Show workload estimation. | 3 | TA Survey
TA-07 | Online Communication | As a TA Applicant, I want to support online communication with staff, So that I can ask questions about the job. | Could Have | 3 | 1. Send messages to staff. 2. View message history. | 5 | TA Survey
TA-08 | Calculate Working Hours | As an employed TA, I want the system to calculate my working hours, So that I can track my pay. | Could Have | 2 | 1. Log hours worked. 2. Generate total hours report. | 3 | TA Survey
TA-09 | Request Leave | As an employed TA, I want to apply for leave for my assigned tasks, So that I can manage my schedule. | Could Have | 4 | 1. Submit leave request. 2. Display request status. | 2 | TA Survey
MO-01 | Post Job Vacancies | As an MO, I want to post jobs with specific requirements, So that I can recruit TAs efficiently. | Must Have | 1 | 1. MO can create a job posting. 2. Job includes required skills. | 3 | core function
MO-02 | View Applicant List | As an MO, I want to view all applicants in a unified list, So that I can easily compare their profiles. | Could Have | 3 | 1. Dashboard shows applicants for the MO's module. 2.CVs are directly accessible. | 5 | MO Survey
MO-03 | Select Applicants | As an MO, I want to select applicants for jobs (accept/reject), So that I can finalize my TA recruitment. | Must Have | 1 | 1. MO can click accept/reject for each applicant. 2.System updates applicant status. | 3 | core function
MO-04 | Export TA List | As an MO, I want to export a final list of confirmed TAs as a CSV file, So that I can share the roster easily. | Could Have | 3 | 1. Button to download CSV. 2. CSV contains confirmed TAs' details. | 2 | MO Survey
MO-05 | AI Skill Matching | As an MO, I want the AI to match skills between jobs and applicants, So that I can quickly identify top candidates. | Should Have | 2 | 1. System calculates matching score. 2. Score is displayed on the applicant list. | 5 | AI Feature
MO-06 | AI Missing Skills Identify | As an MO, I want the AI to automatically identify and highlight the key skills an applicant is missing, So that I can quickly assess their skill gaps without manual cross-checking. | Should Have | 2 | 1. System compares applicant profile with job requirements. 2. Missing skills are clearly highlighted on the MO dashboard. | 5 | AI Feature
AD-01 | Check TA Overall Workload | As an Admin, I want to check TAs' overall workload across all modules, So that I can identify if any single TA has taken on excessive positions. | Must Have | 1 | 1. Dashboard lists all TAs and their total assigned hours/modules. 2. Visually flags TAs who exceed workload limits. | 5 | core function
AD-02 | Global Vacancy Dashboard | As an Admin, I want a global overview of which modules are still unfilled, So that I can monitor university-wide recruitment progress. | Should Have | 2 | 1. Dashboard lists all modules. 2. Displays required TA headcount for each module. | 3 | Admin Survey
AD-03 | Manage Overloaded Tas | As an Admin, I want to force dismiss or transfer positions for overloaded TAs, So that I can enforce workload limits and resolve conflicts. | Could Have | 4 | 1. Admin can manually remove a TA from a specific module 2. System instantly updates module vacancy and TA workload. | 3 | Admin Survey
AD-04 | Export Final Hiring List | As an Admin, I want to quickly export the final hiring list, So that I can process data reports and administrative tasks. | Should Have | 2 | 1. Provide a "One-click Export" button. 2. Generates CSV/Excel with confirmed TA allocations. | 2 | Admin Survey
AD-05 | AI Workload Balancing | As an Admin, I want the AI to intelligently analyze allocations and provide workload balancing suggestions, So that I can optimally distribute TA resources. | Could Have | 3 | 1. AI detects imbalanced distributions across modules 2. System suggests moving specific TAs to balance hours. | 5 | AI Feature